## Dashboard
Project Management Dashboard |  |  |  |  | 17-Feb-20 to 6-Mar-20
Project | Task | Manager | Start Date | End Date | Duration | Days comp. | Progress | Budget | Actual | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13
FinTrack Analytics | Task 1 | Ali | 2020-02-18 | 2020-02-26 | 7 | 7 | 100% | 293000 | 273001
| Task 2 | Fatima | 2020-02-17 | 2020-02-27 | 9 | 4 | 44.44% | 224000 | 57910
| Task 3 | Usman | 2020-02-18 | 2020-02-27 | 8 | 0 | 0% | 978000 | 0
| Task 4 | Bilal | 2020-02-20 | 2020-02-28 | 7 | 3 | 42.86% | 932000 | 379157
| Task 5 | Zainab | 2020-02-21 | 2020-02-26 | 4 | 1 | 25% | 854000 | 322812
| Task 6 | Ali | 2020-02-21 | 2020-02-28 | 6 | 3 | 50% | 81000 | 38461
| Task 7 | Fatima | 2020-02-24 | 2020-03-02 | 6 | 5 | 83.33% | 169000 | 136468
| Task 8 | Usman | 2020-02-25 | 2020-02-28 | 4 | 1 | 25% | 61000 | 12078
| Task 9 | Bilal | 2020-02-27 | 2020-03-06 | 7 | 3 | 42.86% | 645000 | 273048
| Task 10 | Zainab | 2020-02-17 | 2020-02-19 | 3 | 3 | 100% | 68000 | 64987
Grand Total | [7 empty] | 4305000 | 1557922
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
49%

## Workings
Budget v Actual Doughnut & Bar Chart |  |  | Tasks Bar Chart |  |  | Overall Progress - Days Completed v Duration Doughnut Chart |  |  |  |  | Scroll bar position
| Actual | Budget | Not Started | 1 | =COUNTIF(Dashboard!H6:H51,"="&0) | Values |  | Doughnut Chart | % | Formula | 0
Bar Chart | 1557922 | 4305000 | In Progress | 7 | =COUNTIFS(Dashboard!H6:H51,"<>"&0,Dashboard!H6:H51,"<"&1) | Days completed | 30 | Days Completed | 49.18% | =J3/$J$4
Dougnut Chart | 36.19% | 63.81% | Completed | 2 | =COUNTIF(Dashboard!H6:H51,"="&1) | Duration | 61 | Days Remaining | 50.82% | =1-M3
|  | =1-B4 | Remaining | 8 | =F3+F2
|  |  | Total Tasks | 10 | =COUNTA(Dashboard!B6:B50)

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
NexusHR | Task 1 | Ali | 2020-02-17 | 5 | 2020-02-21 | 2 | 40% | 218000 | 97337
NexusHR | Task 2 | Fatima | 2020-02-17 | 6 | 2020-02-24 | 3 | 50% | 393000 | 177440
NexusHR | Task 3 | Usman | 2020-02-18 | 10 | 2020-03-02 | 4 | 40% | 86000 | 31046
NexusHR | Task 4 | Bilal | 2020-02-21 | 9 | 2020-03-04 | 3 | 33.33% | 732000 | 261324
NexusHR | Task 5 | Zainab | 2020-02-17 | 4 | 2020-02-20 | 1 | 25% | 492000 | 116850
NexusHR | Task 6 | Ali | 2020-02-20 | 6 | 2020-02-27 | 0 | 0% | 188000 | 0
NexusHR | Task 7 | Fatima | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 180000 | 79380
NexusHR | Task 8 | Usman | 2020-02-24 | 5 | 2020-02-28 | 2 | 40% | 582000 | 195231
NexusHR | Task 9 | Bilal | 2020-02-24 | 9 | 2020-03-05 | 1 | 11.11% | 562000 | 74746
NexusHR | Task 10 | Zainab | 2020-02-24 | 6 | 2020-03-02 | 3 | 50% | 416000 | 175015
FinTrack Analytics | Task 1 | Ali | 2020-02-18 | 7 | 2020-02-26 | 7 | 100% | 293000 | 273001
FinTrack Analytics | Task 2 | Fatima | 2020-02-17 | 9 | 2020-02-27 | 4 | 44.44% | 224000 | 57910
FinTrack Analytics | Task 3 | Usman | 2020-02-18 | 8 | 2020-02-27 | 0 | 0% | 978000 | 0
FinTrack Analytics | Task 4 | Bilal | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 932000 | 379157
FinTrack Analytics | Task 5 | Zainab | 2020-02-21 | 4 | 2020-02-26 | 1 | 25% | 854000 | 322812
FinTrack Analytics | Task 6 | Ali | 2020-02-21 | 6 | 2020-02-28 | 3 | 50% | 81000 | 38461
FinTrack Analytics | Task 7 | Fatima | 2020-02-24 | 6 | 2020-03-02 | 5 | 83.33% | 169000 | 136468
FinTrack Analytics | Task 8 | Usman | 2020-02-25 | 4 | 2020-02-28 | 1 | 25% | 61000 | 12078
FinTrack Analytics | Task 9 | Bilal | 2020-02-27 | 7 | 2020-03-06 | 3 | 42.86% | 645000 | 273048
FinTrack Analytics | Task 10 | Zainab | 2020-02-17 | 3 | 2020-02-19 | 3 | 100% | 68000 | 64987
RetailFlow ERP | Task 1 | Ali | 2020-02-17 | 10 | 2020-02-28 | 5 | 50% | 839000 | 406974
RetailFlow ERP | Task 2 | Fatima | 2020-02-21 | 5 | 2020-02-27 | 4 | 80% | 729000 | 487139
RetailFlow ERP | Task 3 | Usman | 2020-02-24 | 7 | 2020-03-03 | 3 | 42.86% | 826000 | 298186
RetailFlow ERP | Task 4 | Bilal | 2020-02-26 | 7 | 2020-03-05 | 2 | 28.57% | 895000 | 280583
RetailFlow ERP | Task 5 | Zainab | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67% | 341000 | 129785
HealthDesk App | Task 1 | Ali | 2020-03-02 | 9 | 2020-03-12 | 8 | 88.89% | 787000 | 727188
HealthDesk App | Task 2 | Fatima | 2020-03-02 | 10 | 2020-03-13 | 2 | 20% | 228000 | 47880
HealthDesk App | Task 3 | Usman | 2020-02-17 | 4 | 2020-02-20 | 0 | 0% | 147000 | 0
HealthDesk App | Task 4 | Bilal | 2020-02-19 | 8 | 2020-02-28 | 5 | 62.5% | 338000 | 205123
HealthDesk App | Task 5 | Zainab | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 857000 | 305949
HealthDesk App | Task 6 | Ali | 2020-02-25 | 6 | 2020-03-03 | 3 | 50% | 602000 | 322371
HealthDesk App | Task 7 | Fatima | 2020-02-25 | 4 | 2020-02-28 | 2 | 50% | 990000 | 451440
EcoLogix CRM | Task 1 | Usman | 2020-02-28 | 8 | 2020-03-10 | 3 | 37.5% | 96000 | 32256
EcoLogix CRM | Task 2 | Bilal | 2020-03-02 | 9 | 2020-03-12 | 4 | 44.44% | 513000 | 226233
EcoLogix CRM | Task 3 | Zainab | 2020-02-20 | 5 | 2020-02-26 | 3 | 60% | 616000 | 401579
EcoLogix CRM | Task 4 | Ali | 2020-02-19 | 3 | 2020-02-21 | 3 | 100% | 817000 | 807069
EcoLogix CRM | Task 5 | Fatima | 2020-02-21 | 7 | 2020-03-02 | 3 | 42.86% | 372000 | 173166
EcoLogix CRM | Task 6 | Usman | 2020-02-24 | 10 | 2020-03-06 | 2 | 20% | 50000 | 8400
EcoLogix CRM | Task 7 | Bilal | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 807000 | 262679
EcoLogix CRM | Task 8 | Zainab | 2020-02-24 | 3 | 2020-02-26 | 0 | 0% | 691000 | 0
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)